## Sheet1
Sprint Backlog DuLichDoDay
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Log in-register | 60 | Thiện
The interface |  |  |  | 10 | 0 | 0 | 3 | 3 | 0 | 0
Function |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0
Home | 70 | Phúc | [6 empty] | 0
The interface |  |  |  | 10 | 0 | 5 | 2 | 0 | 0 | 0
Map |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Search |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
See info-book tour |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Message Board | 70 | Hòa
The interface |  |  |  | 10 | 0 | 4 | 2 | 0 | 0 | 0
Đăng tin mới |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
View this post |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Comment-like-dislike |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Tour DL | 70 | Phúc - Hòa
The interface |  |  |  | 10 | 0 | 3 | 3 | 0 | 0 | 0
Filter by price |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Filter by region |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
See info-book tour |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Personal page | 75 | Nhàn
The interface |  |  |  | 10 | 0 | 4 | 4 | 4 | 0 | 0
See info-update information |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
To change the password |  |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0
List of tour-tour has put deletion |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Log |  |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
Tour operators | 75 | Nghiệp - Hoàng
The interface |  |  |  | 10 | 0 | 4 | 4 | 3 | 0 | 0
See info-update information |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Edit post |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
List of tour bookings |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Log |  |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 415 | 0 | 20 | 18 | 10 | 0 | 0