## Sheet1
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | Yes | Yes | High | Complete | 120 | No
Log in-register | Yes | Yes | High | Complete | 20 | Yes
Home | Yes | Yes | High | Complete | 20 | Yes
Message Board | Yes | Yes | Low | Complete | 20 | Yes
Tour DL | Yes | Yes | Medium | Complete | 20 | Yes
Personal page | Yes | Yes | Medium | Complete | 20 | Yes
Tour operators | Yes | Yes | Medium | Complete | 20 | Yes
Sprint 2 | Yes | Yes | Medium | Not Started | 160 | Yes
Login-register-log | Yes | Yes | High | Not Started | 20 | Yes
Message Board-> Like-comment | Yes | Yes | Low | Not Started | 20 | Yes
DL-tour tour > | Yes | Yes | Medium | Not Started | 20 | Yes
Home-> Map, most recent tour | Yes | Yes | High | Not Started | 20 | Yes
Personal page-> change password, delete the set tour | Yes | Yes | Low | Not Started | 20 | Yes
Airline travel page-> edit information | Yes | Yes | Medium | Not Started | 20 | Yes
Trang Cá nhân -> chỉnh sửa thông tin | Yes | Yes | Medium | Not Started | 20 | Yes
Airline travel page-delete, tour, tour more > page tour | Yes | Yes | High | Not Started | 20 | Yes
Sprint 3 | Yes | Yes | High | Not Started | 20 | Yes
FireBase | Yes | No | High | Not Started | 20 | No

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started