## TestExecution
This function will be implemented after we would have defined COMPLEXITY & WEIGHT | [5 empty] | Test Execution
Estimated Execution Time |  | <Build> | [9 empty] | Build_X | Build_1 | Build_2 | Build_3 | Build_4 | Build_5
[6 empty] | #TC passed |  |  |  | 0 |  | 0 | 0 | 1 | 0 | 0 | 13
Complexity | Weight | #Test cases | Est. Time |  |  | #TC failed |  |  |  | 0 |  | 0 | 2 | 0 | 1 | 0 | 0
1 | 5 | - | - |  |  | #TC blocked |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2 | 10 | - | - |  |  | #TC N/A |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
3 | 15 | - | - |  |  | #TC executed |  |  |  | 0 |  | 0 | 2 | 1 | 1 | 0 | 13
4 | 20 | - | - |  |  | %TC passed rate |  |  |  | 0% |  | 0% | 0% | 100% | 0% | 0% | 100%
Total |  |  | - |  |  | % FT coverage |  |  |  | 0% |  | 0% | 15.38% | 7.692% | 7.692% | 0% | 100%
[6 empty] | %Done As Plan | [5 empty] | #DIV/0! | 100% | 50% | 50% | 0% | 100%
[11 empty] | #TCs : | 0 | 2 | 2 | 2 | 2 | 13
Sprint | User Story ID | TC ID | Complexity | Title | Area | Preconditions | Steps | Expected Results | Priority | Final Test Result | Bug IDs | Test Result(*) | Test Result(*) | Test Result(*) | Test Result(*) | Test Result(*) | Test Result(*)
Login screen
1 |  |  |  | Check UI | Login screen | Account has been created successfully | Check UI | All items are designed like with latest design - Email address - Password - Login button | HIGH |  |  |  | FAILED | SELECTED | FAILED | SELECTED | PASSED
Create New Account
1 |  |  |  | Check UI | Create New Account | Account has been created successfully | Check UI | All items are designed like with latest design - Email address - Password - Create account button | HIGH |  |  |  | FAILED | PASSED | SELECTED | SELECTED | PASSED
Home Screen
1 |  |  |  | Check UI | Home Screen |  | Check UI | All items are designed like with latest design - Map - Search | HIGH | [7 empty] | PASSED
New feed screen
1 |  |  |  | Check UI | New feed screen |  | Check UI | All items are designed like with latest design | HIGH | [7 empty] | PASSED
Tour Screen
1 |  |  |  | Check UI | Tour Screen |  | Check UI | 'All items are designed like with latest design | HIGH | [7 empty] | PASSED
User screen
1 |  |  |  | Check UI | User screen |  | Check UI | 'All items are designed like with latest design | HIGH | [7 empty] | PASSED
Edit tour screen
1 |  |  |  | Check UI | Edit tour screen |  | Check UI | 'All items are designed like with latest design | HIGH | [7 empty] | PASSED
Edit post
1 |  |  |  | Check UI | Edit post |  | Check UI | 'All items are designed like with latest design | HIGH | [7 empty] | PASSED
Add tour
1 |  |  |  | Check UI | Add tour |  | Check UI | 'All items are designed like with latest design | HIGH | [7 empty] | PASSED
Update user info
1 |  |  |  | Check UI | Update user info |  | Check UI | 'All items are designed like with latest design | HIGH | [7 empty] | PASSED
Manager tour
1 |  |  |  | Check UI | Manager tour |  | Check UI | 'All items are designed like with latest design | HIGH | [7 empty] | PASSED
Change password
1 |  |  |  | Check UI | Change password |  | Check UI | 'All items are designed like with latest design | HIGH | [7 empty] | PASSED
Manager booking tour screen
1 |  |  |  | Check UI | Manager booking tour screen |  | Check UI | 'All items are designed like with latest design | HIGH | [7 empty] | PASSED
Note on K14: Linh Tran: Final test result is the result of the last execution of the test case
Add New Build
Update Test Result
Run Estimation

## Appendix (hidden)
Build
Ratio of defects to test cases | Green (<) | Yellow | Red (>=)
Critical (Openned + Verify Failed + Re-Openned) / Executed | 1% | 1-3% | 3%
Major (Openned + Verify Failed + Re-Openned)/ Executed | 3% | 3%-10% | 10%
Medium(Openned + Verify Failed + Re-Openned) / Executed | 10% | 10%-20% | 20%
Minor (Openned + Verify Failed + Re-Openned)/ Executed | 20% | >=20% | N/A
Blocked Test Case/ Executed test case | 5% | 5%-30% | 30%
Release
Ratio of defects to test cases | Green (<) | Yellow | Red (>=)
Critical (Pending)/ Executed | 1% | 1-3% | 3%
Major (Pending)/ Executed | 3% | 3%-10% | 10%
Medium(Pending) / Executed | 10% | 10%-20% | 20%
Minor (Pending)/ Executed | 20% | >=20% | N/A
Blocked Test Case/ Executed test case | 5% | 5%-30% | 30%
#Executed Test cases = #Passed Test cases+ #Failed Test cases
Pass rate = #Passed Test cases / #Executed Test Cases
% FT Coverage = #Executed Test Cases / # Planned Test cases

## TestReport_Build_1
Test Report
Project | #REF!
Sprint | 1
Build | 1
Devices | Web
Date | 2014-07-17 |  | 2014-07-17
OS version
Actual Effort (hours) | 7
Testing (TCs) | Passed | Failed | Blocked | N/A (Invalid TCs) | Executed | %Blocked TCs | %TC passed rate | % FT coverage
Build_1 | 105 | 16 | 0 | 0 | 121 | 0% | 0% | 15.38%
Verification (CR) | Opened | Verify Failed | Verify Passed | Re-Openned | Pending | Ratio of defects to executed test cases |  | Rating
Critical | [5 empty] | 0% |  | Yellow
Major | 4 |  |  |  | 4 | 3.306%
Medium | 12 |  |  |  | 12 | 9.917%
Minor | [5 empty] | 0%
Total | 16 | 0 | 0 | 0 | 16
Issue
Highlight
Suggestion/Enhancement

## TestReport_Build_2
Test Report
Project | #REF!
Sprint | 1
Build | 2
Devices | Web
Date | 2014-07-21 |  | 2014-07-21
OS version | Web
Actual Effort (hours) | 3
Testing (TCs) | Passed | Failed | Blocked | N/A (Invalid TCs) | Executed | %Blocked TCs | %TC passed rate | % FT coverage
Build_2 | 96 | 7 | 0 | 0 | 103 | 0% | 100% | 7.692%
Verification (CR) | Opened | Verify Failed | Verify Passed | Re-Openned | Pending | Ratio of defects to executed test cases |  | Rating
Critical | [5 empty] | 0% |  | Green
Major |  |  | 3 |  | 1 | 0%
Medium | 6 | 2 | 7 |  | 11 | 7.767%
Minor | 1 |  |  |  | 1 | 0.9709%
Total | 7 | 2 | 10 | 0 | 13
Issue
Highlight
Suggestion/Enhancement | 202677

## Sheet1
Test Report
Project | #REF!
Sprint | 1
Build | 3
Devices | Web
Date | 2014-07-21 |  | 2014-07-21
OS version | Web
Actual Effort (hours) | 3
Testing (TCs) | Passed | Failed | Blocked | N/A (Invalid TCs) | Executed | %Blocked TCs | %TC passed rate | % FT coverage
Build_3 | [5 empty] | #DIV/0! | 0% | 7.692%
Verification (CR) | Opened | Verify Failed | Verify Passed | Re-Openned | Pending | Ratio of defects to executed test cases |  | Rating
Critical | [5 empty] | #DIV/0! |  | #DIV/0!
Major |  |  | 3 |  | 1 | #DIV/0!
Medium | 6 | 2 | 7 |  | 11 | #DIV/0!
Minor | 1 |  |  |  | 1 | #DIV/0!
Total | 7 | 2 | 10 | 0 | 13
Issue
Highlight
Suggestion/Enhancement | 202677