## Sheet1
Agile Project Plan
Project Name | That Travel Here
Project Manager | Hoang Nghiep
Project Deliverable
Scope Statement
Start Date | 2018-04-04
End Date | 2018-05-22
Overall Progress | 0%
Task Name | Responsible | Start | End | Days | Status
Sprint 1 | Hoang Nghiep | 2018-04-04 | 2018-04-17 | 13 | In progress
Log in-register | Hoàng Thiện | 2018-04-04 | 2018-04-17 | 13 | In progress
Home | Hoàng Phúc | 2018-04-09 | 2018-04-17 | 8 | In progress
Message Board | Ngô Hòa | 2018-04-04 | 2018-04-17 | 13 | In progress
Tour DL | Hoàng Phúc | 2018-04-04 | 2018-04-17 | 13 | In progress
Personal page | Minh Nhàn | 2018-04-04 | 2018-04-17 | 13 | In progress
Tour operators | Công Hoàng - Hoàng Nghiệp | 2018-04-04 | 2018-04-17 | 13 | In progress
Sprint 2 | Minh Nhàn | 2018-04-18 | 2018-05-07 | 19 | Not started
Login-register-log | Hoàng Thiện | 2018-04-18 | 2018-04-24 | 6 | Not started
Message Board-> Like-comment | Ngô Hòa | 2018-04-18 | 2018-04-26 | 8 | Not started
DL-tour tour > | Hoàng Phúc | 2018-04-18 | 2018-04-23 | 5 | Not started
Home-> Map, most recent tour | Hoàng Phúc | 2018-04-24 | 2018-05-07 | 13 | Not started
Personal page-> change password, delete the set tour | Minh Nhàn | 2018-04-18 | 2018-04-24 | 6 | Not started
Airline travel page-> edit information | Công Hoàng | 2018-04-18 | 2018-04-23 | 5 | Not started
Personal page-> edit information | Công Hoàng | 2018-04-24 | 2018-05-02 | 8 | Not started
Airline travel page-delete, tour, tour more > page tour | Hoàng Nghiệp | 2018-04-18 | 2018-05-07 | 19 | Not started
Sprint 3 | Hoàng Phúc | 2018-05-08 | 2018-05-21 | 13 | Not started
FireBase | Group | 2018-05-08 | 2018-05-21 | 13 | Not started
Formulas:
Start = [Start, row below]
End = [End, row below]

## Sheet2
This section is for the drop-down list
Complete
Overdue
In progress
Not started