## Sheet1
Agile Project Plan
Project Name | DuLichDoDay
Project Manager | Hoang Nghiep
Project Deliverable
Scope Statement
Start Date | 2018-04-04
End Date | 2018-05-22
Overall Progress | 0%
Task Name | Responsible | Start | End | Days | Status
Sprint 1 | Hoang Nghiep | 2018-04-04 | 2018-04-17 | 13 | Not started
Đăng nhập - đăng ký | Hoang Thien | 2018-04-04 | 2018-04-10 | 6 | Not started
Trang chủ | Hoang Phuc | 2018-04-09 | 2018-04-17 | 8 | Not started
Bảng tin | Ngo Hoa | 2018-04-04 | 2018-04-17 | 13 | Not started
Tour DL | Hoang Phuc | 2018-04-04 | 2018-04-09 | 5 | Not started
Trang cá nhân | Minh Nhan | 2018-04-04 | 2018-04-17 | 13 | Not started
Hãng du lịch | Cong Hoang - Hoang Nghiep | 2018-04-04 | 2018-04-17 | 13 | Not started
Sprint 2 | Minh Nhàn | 2018-04-18 | 2018-05-02 | 14 | Not started
Đăng nhập - đăng ký - Đăng xuất | Thiện | 2018-04-18 | 2018-04-24 | 6 | Not started
Trang chủ -> Map, đặt tour | Phúc | 2018-04-26 | 2018-05-02 | 6 | Not started
Bảng tin -> Like-comment | Hòa | 2018-04-18 | 2018-04-26 | 8 | Not started
Tour DL -> đặt tour | Phúc | 2018-04-18 | 2018-04-24 | 6 | Not started
Trang Cá nhân -> đổi mật khẩu, xóa tour đặt | Nhàn | 2018-04-18 | 2018-04-24 | 6 | Not started
Trang Cá nhân -> chỉnh sửa thông tin | Hoàng | 2018-04-18 | 2018-04-23 | 5
Trang Hãng du lịch -> chỉnh sửa thông tin | Hoàng | 2018-04-24 | 2018-05-02 | 8 | Not started
Trang Hãng du lịch -> thêm tour, xóa tour, sửa tour | Nghiệp | 2018-04-18 | 2018-05-02 | 14 | Not started
Sprint 3 | Phúc | 2018-05-03 | 2018-05-16 | 13 | Not started
FireBase | Nhóm | 2018-05-03 | 2018-05-16 | 13 | Not started
Formulas:
Start = [Start, row below]
End = [End, row below]